## Project Data
Parks Project Number | Project Name | Project Type | Project Manager | Project Estimate at Completion | Design Start Date | Design Finish Date | Construction Start Date | Construction Finish Date | Milestones | Account Numbers
100001 | New Slide at North Lakes South Park | New Construction | Jimmy Dean | 150000 | 2020-04-29 | 2020-08-12 | 2020-08-27 | 2020-10-01 | Got project approved by Council | 103456100, 426543402, 428877300
100002 | Sidewalk Reconstruction at Briercliff Park | Repair/Maintenance | Frank Sinatra | 756250 | 2019-09-02 | 2020-06-08 | 2020-06-10 | 2021-01-25 | Submitted AIS to Council | 354598200, 322233708
100003 | New Awnings for Golf Driving Range | New Construction | Jimmy Dean | 250800 | 2020-03-02 | 2020-04-04 | 2020-05-01 | 2020-06-30 | Project reached 50% completion. | 103456100
100004 | Cat Park on Elm Street | Bond Project | Joey Schmoey | 1500000 | 2020-07-22 | 2020-11-16 | 2021-02-03 | 2022-05-23 | Land was secured by Real Estate on 5/20/2020. | 107654100, 427755100, 427865471, 320453561, 103676402, 422938708
100005 | Downtown Water Park | New Construction | Marilyn Monroe | 2650225 | 2018-10-30 | 2019-05-29 | 2019-09-09 | 2021-02-15 | Construction RFPs have been released by Purchasing. We are waiting on the solicitation of bids. | 255664517, 426456517
100006 | Sidewalk Path along Cooper Creek Woods | Bond Project | Hank Hill | 12000000 | 2020-05-10 | 2020-11-04 | 2020-11-10 | 2022-03-29 | Engineering firm was selected through procurement process and has started the design. | 107777402, 429876708, 351234100

## Financial Data
Account Numbers | Budget | Expenditures | Encumbered
103456100 | 55876.64 | 10000 | 9000
426543402 | 33000 | 12500 | 10000
428877300 | 10000 | 9921.45 | 9000.28
354598200 | 500000 | 500000 | 108.66
322233708 | 251234.03 | 200000 | 105000
103456100 | 260000 | 125446 | 77.89
107654100 | 500000 | 500000.76 | 312.85
427755100 | 250000 | 125750 | 10000
427865471 | 250000 | 249987 | 75145
320453561 | 100000 | 100000 | 11209.28
103676402 | 54987.55 | 55000 | 1.25
422938708 | 125000 | 133000 | 987.44
255664517 | 1750000 | 250000 | 125
426456517 | 312000 | 0 | 0
107777402 | 250000 | 240123 | 10000
429876708 | 125000 | 54987.26 | 25998.12
351234100 | 1000000 | 80234.99 | 100.23